## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 48 x 5) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123 | 114 | 105 | 96 | 87 | 78 | 69 | 60 | 51 | 42 | 33 | 24 | 15 | 6 | 0 | Ideal Burndown
|  |  | 240 | 2018-04-01: 0; 2018-04-02: 0; 2018-04-03: 0; 2018-04-04: 0; 2018-04-05: 0; 2018-04-06: 0; 2018-04-07: 0; 2018-04-08: 0; 2018-04-09: 0; 2018-04-10: 0; 2018-04-11: 0 | Remaining Hrs (Total)
Development Setup | Github setup | All | 5
| Download / Install Unity | All | 5
| Ramp up on Unity development (Tutorials) | All | 20
Proof of Concept (Level 1) | Get assets for prototype
| UI - Level design (path, player position, enemy position) | Clif
| Enemy movement | Animesh
Item design
| Object collision detection for Player | Watcharit
| Object collision detection for Enemy | Animesh
| Object collision detection for Item | Watcharit
| Player movement | Watcharit
Item usage
| Level background assets | Animesh
| Timer count up | Clif
| Display win/lose | Clif
Finish Game | foo
bar
Team:
Animesh Grover | 12 hours / Week
Clifton Francis | 12 hours / Week
Juan Pinzon Estupinan | 12 hours / Week
Phani Teja Kantamneni | 12 hours / Week
Watcharit Maharutainont | 12 hours / Week
Total Available Hours During Sprint: | 240